## ProjectSchedule
FinGuard AI | [6 empty] | ► Watch How to Make a Gantt Chart in Excel
FinGuard AI — Real-Time Financial Fraud Detection System |  | Project Start: | 2026-08-18
Arnav Kathuria & Akshit Shandilya |  | Today: | 2026-09-15
|  | Display Week: | 1 |  |  | 2026-08-17 | [6 empty] | 2026-08-24 | [6 empty] | 2026-08-31 | [6 empty] | 2026-09-07 | [6 empty] | 2026-09-14 | [6 empty] | 2026-09-21 | [6 empty] | 2026-09-28 | [6 empty] | 2026-10-05
 | time axis 2026-08-17 to 2026-10-11
TASK | ASSIGNED TO | PROGRESS | START | END | DAYS | time axis 2026-08-17 to 2026-10-11
Phase 1: Foundation & Scaffolding (Weeks 1-4)
Project proposal and research proposal | Arnav Kathuria | 100% | 2026-08-18 | 2026-08-25 | 8
Use case diagram and flow diagram | Akshit Shandilya | 100% | 2026-08-26 | 2026-09-01 | 7
Activity diagram, prototyping, and Gantt chart creation | Arnav Kathuria | 100% | 2026-09-02 | 2026-09-08 | 7
Project initialization | Akshit Shandilya | 100% | 2026-09-09 | 2026-09-15 | 7
Phase 2: Rule Engine & Fraud Model (Weeks 5-6)
Rule engine + baseline XGBoost fraud model; risk aggregation and 0-100 scoring | Arnav Kathuria |  | 2026-09-16 | 2026-09-29 | 14
Phase 3: Anomaly Detection & Dashboard (Weeks 7-9)
Isolation Forest anomaly detector; analyst dashboard; parallel detection integration | Akshit Shandilya |  | 2026-09-30 | 2026-10-20 | 21
Phase 4: Explainability & Feedback Loop (Weeks 10-11)
SHAP explainability layer; decision feedback database and retraining loop | Arnav Kathuria |  | 2026-10-21 | 2026-11-03 | 14
Phase 5: Evaluation & Wrap-up (Weeks 12-13)
KPI instrumentation & evaluation (fraud recall, false-positive rate, mean time to detect, analyst productivity, fraud loss avoided) | Akshit Shandilya |  | 2026-11-04 | 2026-11-17 | 14
Buffer week: fixes, final testing, report and demo preparation | Arnav Kathuria |  | 2026-11-18 | 2026-11-24 | 7
Insert new rows ABOVE this one
SIMPLE GANTT CHART by Vertex42.com |  |  |  | 2018-01-13
https://www.vertex42.com/ExcelTemplates/simple-gantt-chart.html
© 2018-2019 Vertex42 LLC
Note on H6: DAYS: This column calculates the duration of the task in calendar days. The duration includes both the Start and End dates.

## About
SIMPLE GANTT CHART by Vertex42.com
https://www.vertex42.com/ExcelTemplates/simple-gantt-chart.html
© 2018-2019 Vertex42 LLC
About This Template
This template provides a simple way to create a Gantt chart to help visualize and track your project. Simply enter your tasks and start and end dates - no formulas required. The bars in the Gantt chart represent the duration of the task and are displayed using conditional formatting. Insert new tasks by inserting new rows.
Additional Help
Click on the link below to visit vertex42.com and learn more about how to use this template, such as how to calculate days and work days, create task dependencies, change the colors of the bars, add a scroll bar to make it easier to change the display week, extend the date range displayed in the chart, etc.
How to Use the Simple Gantt Chart
► Watch How This Gantt Chart Was Created
More Project Management Templates
Visit Vertex42.com to download other project management templates, including different types of project schedules, Gantt charts, tasks lists, etc.
Project Management Templates
About Vertex42
Vertex42.com provides over 300 professionally designed spreadsheet templates for business, home, and education - most of which are free to download. Their collection includes a variety of calendars, planners, and schedules as well as personal finance spreadsheets for budgeting, debt reduction, and loan amortization.
Businesses will find invoices, time sheets, inventory trackers, financial statements, and project planning templates. Teachers and students will find resources such as class schedules, grade books, and attendance sheets. Organize your family life with meal planners, checklists, and exercise logs. Each template is thoroughly researched, refined, and improved over time through feedback from thousands of users.